DATAGOV security workflow_ workshop (early fall 2026)

v 01, prepared by SM

7 July 2026

Goal

- generating and consolidating the DATAGOV security workflow & risk register as a living document, to be revised (bi?)annually

- beyond a technical compliance exercise (e.g., GDPR checklist)

- but combining research practices (“how to"), security (and cybersecurity), data governance, research ethics, critical analysis of our research infrastructure, and mitigation strategies.

Deliverables (*internal)

- Security workflow (narrative, ~5-8 pages to include also in the Ethics WP)

- Risk register (in the form of a spreadsheet)

- Data classification policy (for each type of data, define level of security)

- Access matrix (who has access to what, when, wherem and with what level of permission)

- Incident response procedure (1 page: what to do if/when shit happens)

- New team member onboarding checklist

Process

In six steps; the first three are described below. In an ideal situation, we would meet as a group. Given there is the summer inbetween and Mattéo will soon go to the field, my proposal is to twist the process. I therefore ask each of you to do some homework individually. Individual assignments are marked in yellow; prepare to share in our upcoming workshop.

Deadine for individual assignments: August 30 (for a workshop early September).

TO DO: share ONLY scenarios with Stefi; bring the rest to the workshop

Overview of steps (note  documentation throughout):

- Inventory of DATAGOV “assets”

- Workflow/life cycle of data

- Treat modelling

- Definition of shared security rules

- Assign roles and responsibilities

- Incident workflow

STEP 1: THE INVENTORY: MAP WHAT NEEDS PROTECTING (group, in presence)

TASK: Compile the table (think of all data potentially gathered within DATAGOV, not just your own projcet). Spme basic examples are included; please expand

Example (*not filled entirely to avoid influecing you)

| asset | in DATAGOV | risk if compromised |
| --- | --- | --- |
| Research data | interviews, fieldwork notes, participatory methods data, document analysis… | privacy breach, GDPR violation… |
| People | researchers, research participants, artists… | phishing, harassment, abuse of power… |
| Infrastructure | cloud storage (NextCloud), website/blog, external harddisk, servers (?), university accounts | unauthorized access, breakage, loss, offline… |
| Knowledge | Analysed data, analysis coding schemes, unpublished writings, reviewer comments, artworks, game-based methods/prompts… | intellectual property loss..? |
| Software | scripts, repositories,… | … |

| asset | in DATAGOV | risk if compromised |
| --- | --- | --- |
| Research data | Interviews fieldwork notes | Privacy breach GDPR violation |
| People | Research participants: researchers |  |
| Infrastructure |  |  |
| Knowledge | Coding schemes Unpublished writings Game prompts |  |
| Software |  |  |

STEP 2: MAP THE WORKFLOW/LIFE CYCLE OF EACH ASSET (group, in presence)

Example:

Data collection

↓

Transfer / Deletion from device

↓

Encryption + Storage

↓

Transcription / Cleaning

↓

Analysis

↓

Collaboration + Sharing

↓

Publication

↓

Archiving

↓

[Data deletion]

TASK: For each type of data, and for each step ask:

- Who has access?

- Where is the data?

- Is it encrypted/in a safe space?

- What could go wrong? (doom scenarios welcome)

- What is our mitigation?

Take notes (to share in our upcoming workshop)

Step 3: THREAT MODELLING

TASK: Generating realistic scenarios based on YOUR concrete research plans in the next 12 months. In other words, identify plausible threats that may affect your research activities, data, participants, or the project/team as a whole.

Note down

- What data will you collect? (include also the methods)

- Who will you interact with?

- Where/how is the interaction taking place?

- What digital tools or infrastructures will you use?

Examples of threats:

- Phishing email steals a UvA password.

- Lost laptop, stolen recorder

- Data transfer across border with data on personal devices

- Student assistant downloads participant data onto a personal computer.

- Malicious actors attempt to obtain sensitive interview data

For every threat record (e.g.):

- likelihood

- impact

- mitigation

- responsible person

It is also worth asking ourselves

- Who becomes visible through this process/infrastructure?

- Who is rendered invisible?

- Could security measures themselves produce exclusion or create barriers for vulnerable groups (e.g., contact interviewees on Signal when they use Whatsapp)?

- What new dependencies are created?

- Are research subjects able to contest decisions based on our workflow?

- What assumptions are embedded in the data model?

Fill the table (the example is deliberately wrong):

| Threat scenario | What could happen? | Likelihood (L/M/H) | Impact (L/M/H) | Existing safeguards | Additional mitigation |
| --- | --- | --- | --- | --- | --- |
| My laptop is stolen while travelling for fieldwork. | Interview transcripts become inaccessible or exposed. | Medium | High | Disk encryption, password | Enable remote wipe and avoid storing raw recordings locally. |